## Sheet1
CR_REV_ID | Entry Date | Review by | Detection version | Page/Line/Section/Entity | Open point: description of problem | Proposed Solution | Status
CR_REV_0001 | 2022-10-25 | Esraa Abdelnaby | V1.0 | 1//Table of content/ | Reference Documentation: ……………………………………………1 | This element should be from table of content | Open
CR_REV_0002 | 2022-10-25 | Esraa Abdelnaby | V1.0 | # | Alignment problem | All tables and headers shall be aligned together | Open
CR_REV_0003 | 2022-10-25 | Esraa Abdelnaby | V1.0 | 1//Table of content/Project Description | The name of the forth element is not the same as it's section | Modify " Website Description" to be "Project Description" instead. | Open
CR_REV_0004 | 2022-10-25 | Esraa Abdelnaby | V1.0 | 1//Project Description/Key Elements/ | Dashboard roles requirement is missing. | Please add some customer requirements to describe what needed to be covered for "dashboard roles". | Open
CR_REV_0005 | 2022-10-25 | Esraa Abdelnaby | V1.0 | 1//Mapping Requirements IDs | The table will not be updated | After fixing the previous points, you should update the Mapping Requirements IDs. | Open
CR_REV_0006 | 2022-10-25 | Esraa Abdelnaby | V1.0 | ## | Versions is not updated | * Update document version to be 1.2 * update each modified requiremt's version | Open
CR_REV_0007 | 2022-10-25 | Esraa Abdelnaby | V1.0 | ## | Document History | You should add 2 rows: 1- 1.1 change details 2- 1.2 change details | Open